## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	DataMiners
PROJECT NAME	Purposeful Face
PROJECT MENTOR	Dr Kamal Karlapalem
TEAM MEMBERS	Mohammed Faisal Anees
	Rishabh Sharma
	Mahak Gambhir

## Team_Status
TEAM NAME	DataMiners
PROJECT NAME	Purposeful Face
PROJECT MENTOR	Dr Kamal Karlapalem

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)

Role preferences	Coordination	Faisal	0.5	0.3	Done		0.2	66.6666666667
SVN Repository setup	Preparation	Mahak	1	1.5	Done		-0.5	33.3333333333
Discuss bug report software	Preparation	Rishabh	0	0	Delayed	This is critical to project success	0
Develop questions for requirements elicitation	Documentation	All	3	3.5	Done	Make sure scoping questions are included	-0.5	14.2857142857

Research existing technology	Preparation	All	5	6	Ongoing		-1	16.6666666667
Project synopsis writeup	Documentation	Mahak	1	2	Done		-1	50
Identify role owners	Preparation	Faisal	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	Rishabh	1	2	Done		-1	50
Status tracker	Documentation	Faisal	1		Done
Week 7 (sept 12 - sept 18)

Week 8 (sept 19 - sept 25)

Week 9
Research existing technology		Rishabh,Faisal,Mahak	3	6	Ongoing		-3	50
Status tracker		Rishabh	0.2	0.5	Done
Client Meet		All	0.5	0.5	Done
Preparing the Software Requirements Specification		Mahak	4	3	Done		1	33.3333333333
Week 10

Week 11

Week 12
Research existing technology		Rishabh,Faisal,Mahak	6	12	Ongoing		-6	50
Status tracker		Mahak	0.2	0.1	Done		0.1	100

Week 13
Research existing technology		Rishabh,Faisal,Mahak	7	7	Ongoing		0	0
GUI		Mahak	1	2	Ongoing		-1	50
						-1	50

Week 14
Research existing technology		Rishabh,Faisal,Mahak	6	7	Done		-1	14.2857142857
Status tracker		Mahak	0.2	0.2	Done		0	0
GUI		Mahak	2	2	Ongoing		0	0

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	DataMiners
PROJECT NAME	Purposeful Facebook Account
PROJECT MENTOR	Dr Kamal Karlapalem

Actvities	Mohammed Faisal Anees		Mahak Gambhir		Rishabh Sharma					Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
						0	0
Role preferences	1	0.5	1	0.5	1	0.5					3	1.5
SVN Repository setup			1	1.5					1	1.5
Discuss bug report software					0	0					0	0
Develop questions for requirements elicitation	3	3.5	3	3.5	3	3.5					9	10.5
						0	0
Research existing technology	5	6	5	6	5	6					15	18
Project synopsis writeup			1	2					1	2
Identify role owners	1	0.5	1	0.5	1	1.5					3	2.5
Team Meeting	1	2	1	2	1	2					3	6
Status tracker	2	3					2	3
Week 7 (sept 12 - sept 18)
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 8 (sept 19 - sept 25)
0						0	0
0						0	0
0						0	0
Week 9						0	0
Research existing technology	3	6	1.5	1.5	3	6					7.5	13.5
Client meet	0.5	0.5	0.5	0.5	0.5	0.5
Status Tracker	0	0	0	0	0.2	0.2
Preparing the Software Requirements Specification	0.5	0.5	1	1.5	0.5	0.5					2	2.5
Week 10						0	0
0						0	0
0						0	0
0						0	0
Week 11						0	0
0						0	0
0						0	0
0						0	0
Week 12						0	0
Research existing technology	2	4	2	4	2	4					6	12
Status tracker	0	0	0.2	0.1	0	0					0.2	0.1
0						0	0
0						0	0
Week 13						0	0
Research existing technology	3	3	2	2	3	3					8	8
GUI	0	0	1	2	0	0					1	2
						0	0
						0	0
Week 14						0	0
Research existing technology	2.5	3	1	1	2.5	3					6	7
Status tracker	0	0	0.2	0.2	0	0					0.2	0.2
GUI	0	0	2	2	0	0					2	2
0						0	0
Week 15						0	0
0						0	0
0						0	0
0						0	0
Week 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0